{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["项目绩效目标50万以下"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"项目绩效目标50万以下","index":0,"n_rows":44,"n_cols":6,"rows_kept":44,"merged":[[0,0,0,5],[1,0,1,5],[2,1,2,2],[2,4,2,5],[3,0,4,0],[3,1,4,2],[3,3,4,4],[3,5,4,5],[5,1,5,5],[6,1,6,5],[7,1,7,5],[8,0,41,0],[9,1,35,1],[9,2,16,2],[17,2,19,2],[20,2,27,2],[28,2,35,2],[36,1,41,1],[36,2,38,2],[39,2,41,2],[43,0,43,5]],"flags":["formulas_cached_only"]}
["2022年项目支出绩效目标表"]
["填报单位：（盖章） 衡东县荣桓镇教育管理服务中心                  单位：万元"]
["项目支出名称","校园文化建设、消防备用电源、教学楼维修、围墙抢险、厨具购置、新建食堂及附属工程、一体机更换、设备设施购置、功能室改造、围墙护坡改造、计算机",null,"预算部门","衡东县荣桓镇教育管理服务中心  "]
["年度本级预算金额",145,null,"该项目支出上级资金"]
[]
["项目支出实施期","2022年1-12月"]
["实施期绩效准目标","消除安全隐患，改善教学楼条件"]
["本年度绩效   目标","消除安全隐患，改善办学条件。预计2022年10月完工。"]
["本年度绩效指标","一级指标","二级指标","三级指标","指标值及单位","绩效标准"]
[null,"产出指标","数量指标","校园文化建设","预算计划建设项目","见预算书"]
[{"$nulls":3},"围墙抢险","预算计划建设项目","见预算书"]
[{"$nulls":3},"厨具购置","1套","见预算书"]
[{"$nulls":3},"一体机更换","15台","见预算书"]
[{"$nulls":3},"设备设施购置","10套","见预算书"]
[{"$nulls":3},"功能室改造","预算计划建设项目","见预算书"]
[{"$nulls":3},"围墙护坡改造","预算计划建设项目","见预算书"]
[{"$nulls":3},"计算机","30台","见预算书"]
[null,null,"质量指标","项目竣工验收合格率",{"v":1,"d":"100%"},"行业标准"]
[{"$nulls":3},"维修验收通过率",{"v":1,"d":"100%"},"行业标准"]
[{"$nulls":3},"整改验收通过率",{"v":1,"d":"100%"},"行业标准"]
[null,null,"时效指标","校园文化建设","2022年11月以前","按时完成"]
[{"$nulls":3},"围墙抢险","2022年10月以前","按时完成"]
[{"$nulls":3},"厨具购置","2022年8月以前","按时完成"]
[{"$nulls":3},"一体机更换","2022年7月以前","按时完成"]
[{"$nulls":3},"设备设施购置","2022年8月以前","按时完成"]
[{"$nulls":3},"功能室改造","2022年11月以前","按时完成"]
[{"$nulls":3},"围墙护坡改造","2022年12月以前","按时完成"]
[{"$nulls":3},"计算机","2022年11月以前","按时完成"]
[null,null,"成本指标","校园文化建设","≦33","合同金额"]
[{"$nulls":3},"围墙抢险","≦5","合同金额"]
[{"$nulls":3},"厨具购置","≦5","合同金额"]
[{"$nulls":3},"一体机更换","≦30","合同金额"]
[{"$nulls":3},"设备设施购置","≦8","合同金额"]
[{"$nulls":3},"功能室改造","≦15","合同金额"]
[{"$nulls":3},"围墙护坡改造","≦25","合同金额"]
[{"$nulls":3},"计算机","≦24","合同金额"]
[null,"效益指标","社会效益指标","容纳学生就读率",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[{"$nulls":3},"改善就学条件","有效","有效"]
[{"$nulls":3},"教师入住满意度",{"v":1,"d":"100%"},{"v":1,"d":"100%"}]
[null,null,"社会公众或服务对象满意度指标","师生满意度","≥95%","≥95%"]
[{"$nulls":3},"学生满意度","≥95%","≥94%"]
[{"$nulls":3},"教师满意度","≥95%","≥98%"]
[" "]
["填表人： 罗文婷    联系电话：15197475973     填报日期：2022.5.20    单位负责人签字：龙炳坤"]